## Sheet1
No | Summary | ScreenId | Description | Priority | Reporter | Create date | Due date | Closed date | Assignee | Status
1 | Không đăng nhập được khi sai mật khẩu | SRC_PRODUCT_01 | Steps: 1) Mở màn hình đăng nhập 2) Nhập tài khoản hợp lệ 3) Nhập mật khẩu sai 4) Nhấn Đăng nhập Expected: Hiển thị lỗi sai mật khẩu Actual: Không hiển thị lỗi | High | Tester1 | 2025-12-04
2 | API trả về 500 khi gửi payload lớn | SRC_ORDER_03 | TC_API_015 Steps: Gửi request payload 5MB Expected: Trả về 400 hoặc 413 Actual: Server trả 500 | Critical | Tester2 | 2025-12-04
3 | Nút Lưu không hoạt động trên trình duyệt Safari | SRC_CUSTOMER_02 | TC_UI_021 Steps: Mở trang cập nhật sản phẩm -> Nhấn Lưu Expected: Lưu thành công Actual: Không có phản hồi | Medium | Tester3 | 2025-12-04
4 | Hiển thị sai tổng tiền trong giỏ hàng | SRC_PRINT_01 | TC_CART_009 Expected: Tổng = 250.000 Actual: Hiển thị 200.000 | High | Tester4 | 2025-12-04
5 | Lỗi font chữ trên giao diện mobile | SRC_UI_05 | TC_UI_033 Expected: Font chuẩn Actual: Font fallback trên mobile | Low | Tester5 | 2025-12-04
6 | Upload file >10MB bị treo | SRC_SEARCH_01 | TC_UPLOAD_012 Expected: Upload thành công hoặc báo lỗi Actual: UI đứng, không thông báo | High | Tester6 | 2025-12-04
7 | Không reset form sau khi submit | SRC_STOCK_04 | TC_FORM_004 Expected: Reset form Actual: Dữ liệu vẫn còn | Low | Tester7 | 2025-12-04
8 | Websocket tự ngắt kết nối sau 30 giây | SRC_ORDER_01 | TC_WS_003 Expected: Duy trì kết nối hoặc tự reconnect Actual: Ngắt kết nối sau 30 giây | Medium | Tester8 | 2025-12-04
9 | Không hiển thị thông báo lỗi khi server timeout | SRC_REPORT_02 | TC_ERROR_017 Expected: Hiển thị lỗi timeout Actual: UI chờ mãi không báo lỗi | Medium | Tester9 | 2025-12-04
10 | Không tự động reload dữ liệu sau khi cập nhật | SRC_LOGIN_01 | TC_REFRESH_006 Expected: Reload dữ liệu tự động Actual: Phải nhấn F5 mới thấy thay đổi | Low | Tester10 | 2025-12-04
11 | Thanh toán thất bại khi dùng thẻ Amex | SRC_PAYMENT_01 | TC_PAY_002 Steps: Thanh toán với Amex Expected: Thanh toán thành công Actual: Lỗi gateway trả 402 | High | Tester11 | 2025-12-05
12 | API trả về dữ liệu thiếu trường userId | SRC_API_02 | TC_API_020 Expected: Có trường userId Actual: Trả response thiếu userId | Medium | Tester12 | 2025-12-05
13 | Database deadlock khi insert đồng thời | SRC_DB_01 | TC_DB_001 Steps: Chạy 50 request insert đồng thời Expected: Tất cả insert thành công Actual: Một số request bị deadlock | Critical | Tester13 | 2025-12-05
14 | Load trang chậm (>8s) khi danh sách >1000 items | SRC_PERF_01 | TC_PERF_010 Expected: Load <3s Actual: Load 8-12s | Medium | Tester14 | 2025-12-05
15 | Bảo mật: XSS trên trường comment | SRC_SECURITY_01 | TC_SEC_003 Steps: Gửi payload <script>alert(1)</script> Expected: Dữ liệu được escape Actual: Script executed | Critical | Tester15 | 2025-12-05
16 | Synchronization issue: trạng thái đơn hàng không cập nhật | SRC_INTEGRATION_01 | TC_SYNC_007 Expected: Trạng thái cập nhật sau callback Actual: Trạng thái vẫn cũ | High | Tester16 | 2025-12-05
17 | App mobile crash khi mở ảnh lớn | SRC_MOBILE_01 | TC_MOB_011 Steps: Upload ảnh >8MB Expected: Hiển thị ảnh Actual: App crash | Critical | Tester17 | 2025-12-05
18 | Push notification không gửi tới iOS | SRC_NOTIFICATION_01 | TC_NOTIF_004 Expected: Notification delivered Actual: Không có thông báo trên iOS | Medium | Tester18 | 2025-12-05
19 | Quản lý profile: avatar không lưu | SRC_PROFILE_01 | TC_PROFILE_005 Expected: Avatar lưu và hiển thị Actual: Không lưu | Low | Tester19 | 2025-12-05
20 | Tìm kiếm trả về kết quả không chính xác khi có dấu | SRC_SEARCH_02 | TC_SEARCH_007 Expected: Tìm chính xác với dấu tiếng Việt Actual: Kết quả sai hoặc trống | Medium | Tester20 | 2025-12-05
21 | Không gửi email xác nhận đăng ký | SRC_EMAIL_01 | TC_EMAIL_001 Expected: Gửi email xác nhận Actual: Không có email gửi đi | High | Tester1 | 2025-12-06
22 | Cookie session hết sớm sau 10 phút | SRC_LOGIN_02 | TC_SESSION_002 Expected: Session 60 phút Actual: Session 10 phút | Medium | Tester2 | 2025-12-06
23 | Giao diện dashboard bị phá layout ở Firefox | SRC_UI_06 | TC_UI_045 Expected: Hiển thị đúng trên Firefox Actual: Layout vỡ | Low | Tester3 | 2025-12-06
24 | Export CSV bị lỗi encoding | SRC_REPORT_03 | TC_EXPORT_001 Expected: File UTF-8 Actual: File CP1252 gây lỗi hiển thị tiếng Việt | Medium | Tester4 | 2025-12-06
25 | Tính năng filter không hoạt động khi kết hợp nhiều điều kiện | SRC_FILTER_01 | TC_FILTER_009 Expected: Filter kết hợp đúng Actual: Trả về list nguyên bản | Medium | Tester5 | 2025-12-06
26 | Payment callback double charge | SRC_PAYMENT_02 | TC_PAY_010 Expected: Chỉ charge 1 lần Actual: Charge 2 lần | Critical | Tester6 | 2025-12-06
27 | Timeout khi gọi service bên thứ 3 | SRC_API_03 | TC_API_033 Expected: Retry hoặc trả lỗi rõ ràng Actual: Kết thúc không xử lý | High | Tester7 | 2025-12-06
28 | Autocomplete gợi ý sai từ khóa | SRC_UI_07 | TC_UI_051 Expected: Gợi ý chính xác Actual: Gợi ý không liên quan | Low | Tester8 | 2025-12-06
29 | Không thể xóa item trong giỏ hàng | SRC_CART_02 | TC_CART_005 Expected: Xóa thành công Actual: Item vẫn còn | Medium | Tester9 | 2025-12-06
30 | Sự kiện analytics gửi thiếu thuộc tính | SRC_ANALYTICS_01 | TC_ANALYTICS_003 Expected: Gửi userId và eventType Actual: Thiếu userId | Low | Tester10 | 2025-12-06
31 | API trả header CORS không đúng | SRC_API_04 | TC_CORS_001 Expected: Access-Control-Allow-Origin đúng Actual: Header thiếu | Medium | Tester11 | 2025-12-07
32 | Thanh toán bị từ chối với 3DS | SRC_PAYMENT_03 | TC_PAY_014 Expected: Hỗ trợ 3DS Actual: Không redirect 3DS | High | Tester12 | 2025-12-07
33 | Không lưu trạng thái 'remember me' trên trình duyệt | SRC_LOGIN_03 | TC_LOGIN_010 Expected: Giữ đăng nhập Actual: Logout sau refresh | Low | Tester13 | 2025-12-07
34 | File đính kèm bị hỏng khi tải xuống | SRC_DOWNLOAD_01 | TC_DWN_002 Expected: File intact Actual: File corrupted | High | Tester14 | 2025-12-07
35 | Quản lý quyền: user không có quyền nhưng vẫn truy cập | SRC_AUTH_01 | TC_AUTH_008 Expected: 403 forbidden Actual: Cho phép truy cập | Critical | Tester15 | 2025-12-07
36 | Image lazy-loading không hoạt động | SRC_UI_08 | TC_UI_060 Expected: Lazy load hoạt động Actual: Tải tất cả ảnh cùng lúc | Low | Tester16 | 2025-12-07
37 | Phần mô tả bị cắt ngắn trong email | SRC_EMAIL_02 | TC_EMAIL_009 Expected: Hiển thị đầy đủ mô tả Actual: Bị cắt ở 200 ký tự | Low | Tester17 | 2025-12-07
38 | Không nhận diện barcode trên mobile | SRC_SCAN_01 | TC_SCAN_002 Expected: Nhận diện barcode Actual: Không nhận diện | Medium | Tester18 | 2025-12-07
39 | Form upload multiple file chỉ nhận 1 file | SRC_UPLOAD_02 | TC_UPLOAD_020 Expected: Nhận nhiều file Actual: Chỉ lên 1 file | Medium | Tester19 | 2025-12-07
40 | CRON job không chạy tự động | SRC_CRON_01 | TC_CRON_001 Expected: Cron chạy hàng ngày Actual: Không có lịch trình | High | Tester20 | 2025-12-07
41 | Không hiển thị hình thumb cho sản phẩm mới | SRC_PRODUCT_02 | TC_PRODUCT_010 Expected: Thumb hiển thị Actual: Trống | Low | Tester1 | 2025-12-08
42 | Phiên dịch multi-language thiếu chuỗi | SRC_I18N_01 | TC_I18N_002 Expected: Có chuỗi tiếng Việt Actual: Hiển thị key thay vì text | Low | Tester2 | 2025-12-08
43 | Không theo dõi phiên người dùng đúng cách | SRC_SESSION_03 | TC_SESSION_010 Expected: Theo dõi session chính xác Actual: Session mismatched | Medium | Tester3 | 2025-12-08
44 | Thanh toán bị chậm (>10s) | SRC_PAYMENT_04 | TC_PAY_020 Expected: Response <3s Actual: 10-15s | Medium | Tester4 | 2025-12-08
45 | Export PDF bị lỗi format | SRC_REPORT_04 | TC_PDF_006 Expected: PDF đúng layout Actual: Layout bị vỡ | Low | Tester5 | 2025-12-08
46 | Không nhận diện địa chỉ email hợp lệ | SRC_VALIDATION_01 | TC_VALID_004 Expected: Validate đúng Actual: Nhận email invalid | Low | Tester6 | 2025-12-08
47 | Session fixation vulnerability | SRC_SECURITY_02 | TC_SEC_010 Expected: Không tồn tại session fixation Actual: Vulnerable | Critical | Tester7 | 2025-12-08
48 | Webhook retry không hoạt động | SRC_WEBHOOK_01 | TC_WEB_005 Expected: Retry on failure Actual: Không retry | High | Tester8 | 2025-12-08
49 | Không đồng bộ inventory giữa warehouse | SRC_INVENTORY_01 | TC_INV_002 Expected: Đồng bộ theo real-time Actual: Chậm 30 phút | Medium | Tester9 | 2025-12-08
50 | Autocomplete search crash khi nhập ký tự đặc biệt | SRC_SEARCH_03 | TC_SEARCH_015 Expected: Không crash Actual: UI crash | High | Tester10 | 2025-12-08
51 | Duplicate entries in order history | SRC_ORDER_04 | TC_ORDER_023 Expected: No duplicates Actual: Duplicate rows | Low | Tester11 | 2025-12-09
52 | Missing translation in French locale | SRC_I18N_02 | TC_I18N_007 Expected: French translation Actual: Missing | Low | Tester12 | 2025-12-09
53 | Search ranking irrelevant for product keywords | SRC_SEARCH_04 | TC_SEARCH_020 Expected: Relevant ranking Actual: Irrelevant results | Medium | Tester13 | 2025-12-09
54 | SSL certificate expired on staging | SRC_INFRA_02 | Expected: Valid SSL Actual: Expired certificate | Critical | Tester14 | 2025-12-09
55 | Role-based UI elements visible cho user thiếu quyền | SRC_AUTH_02 | TC_AUTH_023 Expected: Hidden Actual: Visible | High | Tester15 | 2025-12-09
56 | Import CSV skip rows with empty cells | SRC_IMPORT_01 | TC_IMPORT_005 Expected: Import with warnings Actual: Rows skipped silently | Medium | Tester16 | 2025-12-09
57 | Filter by date range lỗi khi start > end | SRC_FILTER_02 | TC_FILTER_015 Expected: Return empty or error Actual: Crash | High | Tester17 | 2025-12-09
58 | Avatar upload không check file type | SRC_PROFILE_02 | TC_PROFILE_010 Expected: Validate file type Actual: Accept any file | Low | Tester18 | 2025-12-09
59 | Mobile layout button chồng nhau trên iPhone 8 | SRC_MOBILE_02 | TC_MOB_020 Expected: Button align Actual: Overlap | Low | Tester19 | 2025-12-09
60 | API rate limit không áp dụng | SRC_API_05 | TC_API_050 Expected: 429 khi vượt limit Actual: No rate limit | Medium | Tester20 | 2025-12-09
61 | Session cookie missing Secure flag | SRC_SECURITY_03 | TC_SEC_014 Expected: Secure cookie Actual: Cookie missing flag | High | Tester1 | 2025-12-10
62 | Export image resolution quá thấp | SRC_MEDIA_02 | TC_MEDIA_011 Expected: High res Actual: Low res | Low | Tester2 | 2025-12-10
63 | Lazy loading ảnh làm flicker trên scroll | SRC_UI_09 | TC_UI_070 Expected: Smooth Actual: Flicker | Low | Tester3 | 2025-12-10
64 | API trả lỗi 401 khi token hợp lệ | SRC_API_06 | TC_API_061 Expected: Token accepted Actual: 401 | High | Tester4 | 2025-12-10
65 | Cache invalidation không hoạt động | SRC_CACHE_01 | TC_CACHE_004 Expected: Cache invalidate Actual: Stale data | Medium | Tester5 | 2025-12-10
66 | Notification email spam do loop | SRC_EMAIL_03 | TC_EMAIL_012 Expected: One email Actual: Multiple emails sent | High | Tester6 | 2025-12-10
67 | Error handling: missing try/catch gây crash | SRC_ERROR_02 | TC_ERROR_021 Expected: Graceful error Actual: Crash app | Critical | Tester7 | 2025-12-10
68 | Profile update race condition | SRC_PROFILE_03 | TC_PROFILE_012 Expected: Last write wins consistently Actual: Occasionally lost update | Medium | Tester8 | 2025-12-10
69 | Mobile keyboard overlaps input field | SRC_MOBILE_03 | TC_MOB_025 Expected: Input visible when keyboard open Actual: Hidden | Low | Tester9 | 2025-12-10
70 | Search suggestions break when DB slow | SRC_SEARCH_05 | TC_SEARCH_030 Expected: Degraded gracefully Actual: JS error thrown | Medium | Tester10 | 2025-12-10
71 | Incorrect VAT calculation at checkout | SRC_TAX_01 | TC_TAX_003 Expected: VAT 10% Actual: Calculated 8% | High | Tester11 | 2025-12-11
72 | Order confirmation email missing order details | SRC_EMAIL_04 | TC_EMAIL_020 Expected: Show order details Actual: Empty body | Medium | Tester12 | 2025-12-11
73 | Legacy browser support broken (IE11) | SRC_UI_10 | TC_UI_080 Expected: Graceful degrade Actual: App unusable | Low | Tester13 | 2025-12-11
74 | Background job leaks memory over time | SRC_INFRA_03 | TC_MEM_001 Expected: Stable memory Actual: Memory growth | High | Tester14 | 2025-12-11
75 | Sorting by price không đúng thứ tự | SRC_CATALOG_01 | TC_SORT_002 Expected: Asc/Desc correct Actual: Wrong order | Low | Tester15 | 2025-12-11
76 | API trả html thay vì json khi lỗi | SRC_API_07 | TC_API_072 Expected: JSON error Actual: HTML error page | Medium | Tester16 | 2025-12-11
77 | File upload progress bar nhảy không chính xác | SRC_UPLOAD_03 | TC_UPLOAD_030 Expected: Accurate progress Actual: Jumping percent | Low | Tester17 | 2025-12-11
78 | Payment refund không hoàn về đúng tài khoản | SRC_PAYMENT_05 | TC_PAY_030 Expected: Refund to original Actual: Refund to system account | High | Tester18 | 2025-12-11
79 | Order export missing VAT fields | SRC_ORDER_05 | TC_EXPORT_010 Expected: Include VAT Actual: Missing fields | Low | Tester19 | 2025-12-11
80 | Image crop tool bị lệch tâm | SRC_MEDIA_03 | TC_MEDIA_020 Expected: Crop centered Actual: Off-center | Low | Tester20 | 2025-12-11
81 | Push notification duplicate when reconnect | SRC_NOTIFICATION_02 | TC_NOTIF_020 Expected: Single notification Actual: Duplicated notifications | Medium | Tester1 | 2025-12-12
82 | Admin panel search không lọc theo role | SRC_ADMIN_01 | TC_ADMIN_005 Expected: Filter by role Actual: No filter | Low | Tester2 | 2025-12-12
83 | Import images bị timeout | SRC_IMPORT_02 | TC_IMPORT_011 Expected: Import complete Actual: Timeout error | High | Tester3 | 2025-12-12
84 | Endpoint health check trả 500 | SRC_HEALTH_01 | TC_HEALTH_001 Expected: 200 OK Actual: 500 Internal Error | Critical | Tester4 | 2025-12-12
85 | Mobile deep link không mở app | SRC_MOBILE_04 | TC_DEEP_002 Expected: Open app Actual: No action | Medium | Tester5 | 2025-12-12
86 | Search facet counts không chính xác | SRC_SEARCH_06 | TC_SEARCH_040 Expected: Correct counts Actual: Mismatch | Low | Tester6 | 2025-12-12
87 | User avatar cache không refresh | SRC_CACHE_02 | TC_CACHE_010 Expected: Update avatar on change Actual: Old avatar shown | Low | Tester7 | 2025-12-12
88 | Webhook payload missing signature | SRC_WEBHOOK_02 | TC_WEB_010 Expected: Include signature Actual: Missing signature | High | Tester8 | 2025-12-12
89 | Email unsubscribe link broken | SRC_EMAIL_05 | TC_EMAIL_030 Expected: Unsubscribe works Actual: 404 page | Low | Tester9 | 2025-12-12
90 | Premium features visible cho user free tier | SRC_AUTH_03 | TC_AUTH_031 Expected: Hidden features Actual: Visible | High | Tester10 | 2025-12-12
91 | UI dark mode bị lỗi contrast | SRC_UI_11 | TC_UI_090 Expected: Readable contrast Actual: Low contrast text | Low | Tester11 | 2025-12-13
92 | Search fuzzy matching không hoạt động | SRC_SEARCH_07 | TC_SEARCH_050 Expected: Fuzzy match Actual: Exact match only | Medium | Tester12 | 2025-12-13
93 | API documentation outdated | SRC_DOCS_01 | TC_DOC_001 Expected: Updated docs Actual: Outdated API spec | Low | Tester13 | 2025-12-13
94 | Mobile app logout unexpectedly after backgrounding | SRC_MOBILE_05 | TC_MOB_040 Expected: Stay logged in Actual: Logout on resume | Medium | Tester14 | 2025-12-13
95 | Form validation allows negative quantities | SRC_FORM_01 | TC_FORM_020 Expected: No negative Actual: Accept negative quantities | Low | Tester15 | 2025-12-13
96 | API returns 206 partial content incorrectly | SRC_API_08 | TC_API_080 Expected: 200 or full 206 Actual: Incorrect partial content | Medium | Tester16 | 2025-12-13
97 | Retry logic causes duplicate order creation | SRC_ORDER_06 | TC_ORDER_035 Expected: Idempotent create Actual: Duplicate orders | High | Tester17 | 2025-12-13
98 | Permissions escalation via crafted request | SRC_SECURITY_04 | TC_SEC_020 Expected: Reject malicious request Actual: Privilege escalation | Critical | Tester18 | 2025-12-13
99 | Background sync not honoring timezone | SRC_SYNC_02 | TC_SYNC_012 Expected: Respect timezone Actual: Sync at wrong hour | Low | Tester19 | 2025-12-13
100 | File preview không render PDF lớn | SRC_PREVIEW_01 | TC_PREVIEW_005 Expected: Render PDF Actual: Fail render | Medium | Tester20 | 2025-12-13
101 | Search indexing delay quá lâu | SRC_INDEX_01 | TC_INDEX_002 Expected: Index within 5m Actual: Delay 2h | Medium | Tester1 | 2025-12-14
102 | Chat service disconnect khi idle | SRC_CHAT_01 | TC_CHAT_008 Expected: Keep alive Actual: Disconnect after idle | Low | Tester2 | 2025-12-14
103 | Order status not updating in webhook retries | SRC_WEBHOOK_03 | TC_WEB_020 Expected: Idempotent updates Actual: Missing updates | High | Tester3 | 2025-12-14
104 | Profile settings not saved on slow network | SRC_PROFILE_04 | TC_PROFILE_020 Expected: Retry or save Actual: Fail silently | Low | Tester4 | 2025-12-14
105 | API returns different schema between environments | SRC_API_09 | TC_API_090 Expected: Consistent schema Actual: Differs between staging/prod | Medium | Tester5 | 2025-12-14
106 | App crash when locale set to Arabic | SRC_I18N_03 | TC_I18N_015 Expected: RTL support Actual: Crash on render | High | Tester6 | 2025-12-14
107 | Search suggestion timeout on high load | SRC_SEARCH_08 | TC_SEARCH_100 Expected: Graceful degrade Actual: Timeout errors | Medium | Tester7 | 2025-12-14
108 | Duplicate email notifications for same event | SRC_EMAIL_06 | TC_EMAIL_040 Expected: Single notification Actual: Duplicates | Low | Tester8 | 2025-12-14
109 | Incorrect rounding in price calculation | SRC_BILLING_01 | TC_BILL_011 Expected: Round to 2 decimals Actual: Rounding error | Low | Tester9 | 2025-12-14
110 | API accepts invalid enum value and crashes downstream | SRC_API_10 | TC_API_100 Expected: Validate enum Actual: Crash downstream | High | Tester10 | 2025-12-14
111 | Slow DB query during peak hours | SRC_DB_02 | TC_DB_020 Expected: Query <200ms Actual: 1-2s | Medium | Tester11 | 2025-12-15
112 | Inconsistent timezone display between UI and emails | SRC_TIME_01 | TC_TIME_002 Expected: Same timezone Actual: Different timezone shown | Low | Tester12 | 2025-12-15
113 | Password reset email link expired too soon | SRC_EMAIL_07 | TC_EMAIL_050 Expected: Link valid 24h Actual: Expires 10m | Medium | Tester13 | 2025-12-15
114 | CSV import trims leading zeros in product codes | SRC_IMPORT_03 | TC_IMPORT_020 Expected: Preserve leading zeros Actual: Trims zeros | Low | Tester14 | 2025-12-15
115 | Cache warmup job fails silently | SRC_CRON_02 | TC_CRON_010 Expected: Warmup success log Actual: Silent failure | Medium | Tester15 | 2025-12-15
116 | App shows deprecated API warning in console | SRC_DEVTOOLS_01 | TC_DEV_001 Expected: No warnings Actual: Deprecated API used | Low | Tester16 | 2025-12-15
117 | Mobile camera permission dialog không bật | SRC_MOBILE_06 | TC_MOB_060 Expected: Request permission Actual: No dialog | Low | Tester17 | 2025-12-15
118 | Order cancellation race causes charge not refunded | SRC_ORDER_07 | TC_ORDER_050 Expected: Refund processed Actual: No refund | High | Tester18 | 2025-12-15
119 | API returns inconsistent content-type header | SRC_API_11 | TC_API_110 Expected: application/json Actual: text/html | Medium | Tester19 | 2025-12-15
120 | Search autocomplete shows stale suggestions | SRC_SEARCH_09 | TC_SEARCH_110 Expected: Fresh suggestions Actual: Stale results | Low | Tester20 | 2025-12-15
121 | Profile picture upload causes memory spike | SRC_MEDIA_04 | TC_MEDIA_030 Expected: Stable memory Actual: Spike and OOM risk | High | Tester1 | 2025-12-16
122 | Admin role cannot access audit logs | SRC_ADMIN_02 | TC_ADMIN_020 Expected: Access audit logs Actual: 403 forbidden | Medium | Tester2 | 2025-12-16
123 | Terms and conditions link broken on footer | SRC_UI_12 | TC_UI_100 Expected: Open T&C Actual: 404 | Low | Tester3 | 2025-12-16
124 | API throttling not per-user | SRC_API_12 | TC_API_120 Expected: Throttle per user Actual: Global throttle | Medium | Tester4 | 2025-12-16
125 | Mobile push badge count incorrect | SRC_NOTIFICATION_03 | TC_NOTIF_050 Expected: Correct badge count Actual: Incorrect number | Low | Tester5 | 2025-12-16
126 | Search filter by color không hoạt động | SRC_SEARCH_10 | TC_SEARCH_130 Expected: Filter by color Actual: No results | Low | Tester6 | 2025-12-16
127 | Order invoice missing tax ID | SRC_ORDER_08 | TC_ORDER_060 Expected: Include tax ID Actual: Missing field | Low | Tester7 | 2025-12-16
128 | Background worker restart không pickup job queue | SRC_WORKER_01 | TC_WORK_010 Expected: Restart recovers queue Actual: Jobs lost | High | Tester8 | 2025-12-16
129 | API health endpoint slow under load | SRC_HEALTH_02 | TC_HEALTH_010 Expected: Fast health check Actual: Slow response | Medium | Tester9 | 2025-12-16
130 | Checkout promo code not applied | SRC_PROMO_01 | TC_PROMO_002 Expected: Discount applied Actual: No discount | Low | Tester10 | 2025-12-16
131 | Error page shows stack trace to user | SRC_ERROR_03 | TC_ERROR_030 Expected: Friendly error page Actual: Stack trace exposed | Critical | Tester11 | 2025-12-17
132 | Image upload accepts executable files | SRC_MEDIA_05 | TC_MEDIA_040 Expected: Validate mime type Actual: Accept executables | Critical | Tester12 | 2025-12-17
133 | Analytics event timestamp off by one hour | SRC_ANALYTICS_02 | TC_ANALYTICS_010 Expected: Accurate timestamp Actual: Off by +1h | Low | Tester13 | 2025-12-17
134 | App shows wrong currency symbol for locale | SRC_UI_13 | TC_UI_110 Expected: Correct currency Actual: Wrong symbol | Low | Tester14 | 2025-12-17
135 | Search indexer skip some languages | SRC_INDEX_02 | TC_INDEX_015 Expected: Index all languages Actual: Skipping certain locales | Medium | Tester15 | 2025-12-17
136 | Payment gateway webhook signature mismatch | SRC_PAYMENT_06 | TC_PAY_040 Expected: Verify signature Actual: Signature mismatch | High | Tester16 | 2025-12-17
137 | Order return flow allows negative refund | SRC_ORDER_09 | TC_ORDER_070 Expected: No negative refund Actual: Negative refund allowed | Low | Tester17 | 2025-12-17
138 | Notification preference toggle không lưu | SRC_NOTIFICATION_04 | TC_NOTIF_060 Expected: Save preference Actual: Reset on reload | Low | Tester18 | 2025-12-17
139 | Search suggestion duplicates entries | SRC_SEARCH_11 | TC_SEARCH_140 Expected: Unique suggestions Actual: Duplicates | Low | Tester19 | 2025-12-17
140 | PDF generation timeouts on large reports | SRC_REPORT_05 | TC_PDF_020 Expected: Generate within time Actual: Timeout | High | Tester20 | 2025-12-17
141 | Account lockout after failed logins not working | SRC_SECURITY_05 | TC_SEC_050 Expected: Lockout after threshold Actual: No lockout | High | Tester1 | 2025-12-18
142 | API pagination returns inconsistent total count | SRC_API_13 | TC_API_130 Expected: Correct total Actual: Inconsistent count | Medium | Tester2 | 2025-12-18
143 | Color contrast fails accessibility test | SRC_A11Y_01 | TC_A11Y_002 Expected: Pass contrast Actual: Fail | Low | Tester3 | 2025-12-18
144 | Mobile offline mode không lưu changes | SRC_MOBILE_07 | TC_MOB_070 Expected: Sync when online Actual: Lost changes | Medium | Tester4 | 2025-12-18
145 | Search fuzzy matches return empty for short queries | SRC_SEARCH_12 | TC_SEARCH_200 Expected: Return suggestions Actual: Empty results | Low | Tester5 | 2025-12-18
146 | Deprecated API still exposed publicly | SRC_API_14 | TC_API_140 Expected: Deprecation warning only to devs Actual: Publicly accessible | Low | Tester6 | 2025-12-18
147 | Profile bio textarea allows script tags | SRC_PROFILE_05 | TC_PROFILE_030 Expected: Strip scripts Actual: Stored script tags | Critical | Tester7 | 2025-12-18
148 | Order tracking link broken in email | SRC_EMAIL_08 | TC_EMAIL_060 Expected: Valid tracking link Actual: 404 | Low | Tester8 | 2025-12-18
149 | Search autocomplete slow on first load | SRC_SEARCH_13 | TC_SEARCH_210 Expected: Fast response Actual: Slow on first request | Low | Tester9 | 2025-12-18
150 | Unexpected logout when switching networks | SRC_SESSION_04 | TC_SESSION_020 Expected: Stay logged in Actual: Logout on network change | Medium | Tester10 | 2025-12-18
151 | Payment page shows expired card message incorrectly | SRC_PAYMENT_07 | TC_PAY_070 Expected: Show correct message Actual: Incorrect expired message | Low | Tester11 | 2025-12-19
152 | API missing Caching headers causing load | SRC_API_15 | TC_API_150 Expected: Cache headers Actual: No-cache headers | Medium | Tester12 | 2025-12-19
153 | Search result snippet cuts words in half | SRC_SEARCH_14 | TC_SEARCH_220 Expected: Snippet intact Actual: Cut mid-word | Low | Tester13 | 2025-12-19
154 | App shows black screen on startup for some devices | SRC_MOBILE_08 | TC_MOB_080 Expected: Normal startup Actual: Black screen | Critical | Tester14 | 2025-12-19
155 | Incorrect stock decrement on partial refund | SRC_INVENTORY_02 | TC_INV_010 Expected: Correct decrement Actual: Wrong amount | High | Tester15 | 2025-12-19
156 | API returns 204 with body causing client error | SRC_API_16 | TC_API_160 Expected: 204 no body Actual: 204 with body | Medium | Tester16 | 2025-12-19
157 | File attachment names with unicode bị lỗi | SRC_DOWNLOAD_02 | TC_DWN_010 Expected: Preserve unicode Actual: Filename corrupted | Low | Tester17 | 2025-12-19
158 | Search suggestions show HTML tags | SRC_SEARCH_15 | TC_SEARCH_230 Expected: Escaped HTML Actual: Raw HTML tags shown | Low | Tester18 | 2025-12-19
159 | Analytics backlog grows unbounded | SRC_ANALYTICS_03 | TC_ANALYTICS_020 Expected: Process backlog Actual: Backlog grows | High | Tester19 | 2025-12-19
160 | Lack of input sanitization on admin endpoints | SRC_ADMIN_03 | TC_ADMIN_030 Expected: Sanitize inputs Actual: Unsanitized input passes | Critical | Tester20 | 2025-12-19
161 | Hotfix deployment not applied to blue env | SRC_DEPLOY_01 | TC_DEPLOY_002 Expected: Both blue/green updated Actual: Only green updated | High | Tester1 | 2025-12-20
162 | Order payment stuck in pending state | SRC_ORDER_10 | TC_ORDER_080 Expected: Move to paid or failed Actual: Stuck pending | High | Tester2 | 2025-12-20
163 | Search filter tag removal fails | SRC_SEARCH_16 | TC_SEARCH_240 Expected: Remove tag filter Actual: Tag remains | Low | Tester3 | 2025-12-20
164 | Mobile app permissions reset after update | SRC_MOBILE_09 | TC_MOB_090 Expected: Preserve permissions Actual: Reset to defaults | Low | Tester4 | 2025-12-20
165 | Tracking pixel not firing on checkout | SRC_TRACKING_01 | TC_TRACK_002 Expected: Pixel fires on checkout Actual: Not firing | Medium | Tester5 | 2025-12-20
166 | API response time spike after midnight | SRC_API_17 | TC_API_170 Expected: Stable response times Actual: Spike after 00:00 | Medium | Tester6 | 2025-12-20
167 | Cart merge logic creates duplicate items | SRC_CART_03 | TC_CART_030 Expected: Merge without duplicates Actual: Duplicate items | Low | Tester7 | 2025-12-20
168 | UI role switch button not visible for admin | SRC_UI_14 | TC_UI_130 Expected: Visible for admin Actual: Hidden | Low | Tester8 | 2025-12-20
169 | Incomplete order refund calculations | SRC_BILLING_02 | TC_BILL_020 Expected: Full refund calculation Actual: Missing fees | High | Tester9 | 2025-12-20
170 | Search phrase highlighting off by index | SRC_SEARCH_17 | TC_SEARCH_250 Expected: Correct highlights Actual: Off-by-one highlighting | Low | Tester10 | 2025-12-20
171 | API rate limit counter resets unexpectedly | SRC_API_18 | TC_API_180 Expected: Persistent counter Actual: Resets unexpectedly | Medium | Tester11 | 2025-12-21
172 | App shows wrong version number in footer | SRC_UI_15 | TC_UI_140 Expected: Correct version Actual: Old version displayed | Low | Tester12 | 2025-12-21
173 | Ordering flow allows negative price coupons | SRC_PROMO_02 | TC_PROMO_010 Expected: Prevent negative price Actual: Allows negative | Low | Tester13 | 2025-12-21
174 | Mobile in-app browser not following redirect | SRC_MOBILE_10 | TC_MOB_100 Expected: Follow redirect Actual: No redirect | Low | Tester14 | 2025-12-21
175 | Search results differ between pagination pages | SRC_SEARCH_18 | TC_SEARCH_260 Expected: Consistent results Actual: Differing results | Medium | Tester15 | 2025-12-21
176 | Order cancel webhook missing reason field | SRC_WEBHOOK_04 | TC_WEB_030 Expected: Include reason Actual: Missing field | Low | Tester16 | 2025-12-21
177 | Password strength meter inaccurate | SRC_SECURITY_06 | TC_SEC_070 Expected: Accurate strength Actual: Overestimates strength | Low | Tester17 | 2025-12-21
178 | API returns stack trace in prod logs | SRC_LOGGING_01 | TC_LOG_002 Expected: No stack in prod Actual: Stack trace logged | High | Tester18 | 2025-12-21
179 | Mobile camera orientation incorrect on capture | SRC_MOBILE_11 | TC_MOB_110 Expected: Correct orientation Actual: Rotated image | Low | Tester19 | 2025-12-21
180 | Search synonyms mapping missing common terms | SRC_SEARCH_19 | TC_SEARCH_270 Expected: Map synonyms Actual: Missing mapping | Low | Tester20 | 2025-12-21
181 | Invalid email stored in database without validation | SRC_VALIDATION_02 | TC_VALID_010 Expected: Reject invalid emails Actual: Stored invalid email | Low | Tester1 | 2025-12-22
182 | Payment gateway downtime not handled | SRC_PAYMENT_08 | TC_PAY_080 Expected: Retry/fallback Actual: Transactions fail without fallback | Critical | Tester2 | 2025-12-22
183 | Background worker uses 100% CPU sporadically | SRC_WORKER_02 | TC_WORK_020 Expected: Stable CPU Actual: Spike to 100% | High | Tester3 | 2025-12-22
184 | Search indexer missing accents normalization | SRC_INDEX_03 | TC_INDEX_030 Expected: Normalize accents Actual: Non-normalized index | Low | Tester4 | 2025-12-22
185 | App shows permission denied on accessing camera | SRC_MOBILE_12 | TC_MOB_120 Expected: Permission requested and granted Actual: Permission denied unexpectedly | Medium | Tester5 | 2025-12-22
186 | Order email subject includes internal token | SRC_EMAIL_09 | TC_EMAIL_070 Expected: No internal tokens Actual: Token exposed in subject | Low | Tester6 | 2025-12-22
187 | API returns inconsistent date format | SRC_API_19 | TC_API_190 Expected: ISO8601 Actual: Mixed formats | Low | Tester7 | 2025-12-22
188 | Mobile app in-app purchases failing | SRC_PAYMENT_09 | TC_PAY_090 Expected: Purchase success Actual: Failure on store validation | High | Tester8 | 2025-12-22
189 | Search fuzzy match weights favor stopwords | SRC_SEARCH_20 | TC_SEARCH_300 Expected: Weight stopwords low Actual: Stopwords overweighted | Low | Tester9 | 2025-12-22
190 | Admin export includes PII fields mistakenly | SRC_ADMIN_04 | TC_ADMIN_040 Expected: Exclude PII Actual: Includes PII columns | Critical | Tester10 | 2025-12-22
191 | PDF viewer memory leak on long documents | SRC_MEDIA_06 | TC_MEDIA_060 Expected: Stable memory Actual: Memory leak | High | Tester11 | 2025-12-23
192 | Order webhook retries not idempotent | SRC_WEBHOOK_05 | TC_WEB_050 Expected: Idempotent retries Actual: Duplicate processing | High | Tester12 | 2025-12-23
193 | App notification permissions blocked permanently after deny | SRC_NOTIFICATION_05 | TC_NOTIF_070 Expected: Allow re-prompt Actual: Permanently blocked | Low | Tester13 | 2025-12-23
194 | Search result caching shows outdated products | SRC_CACHE_03 | TC_CACHE_020 Expected: Fresh products Actual: Outdated cache | Medium | Tester14 | 2025-12-23
195 | Order refund email not sent | SRC_EMAIL_10 | TC_EMAIL_080 Expected: Send refund email Actual: No email sent | Low | Tester15 | 2025-12-23
196 | Mobile deeplink parameter parsing wrong | SRC_MOBILE_13 | TC_MOB_130 Expected: Parse params correctly Actual: Missing params | Low | Tester16 | 2025-12-23
197 | API schema versioning not present | SRC_API_20 | TC_API_200 Expected: Versioned schema Actual: No versioning | Low | Tester17 | 2025-12-23
198 | Search result snippet shows incomplete HTML | SRC_SEARCH_21 | TC_SEARCH_310 Expected: Strip HTML Actual: Partial HTML shown | Low | Tester18 | 2025-12-23
199 | Order export to accounting missing invoice number | SRC_ORDER_11 | TC_ORDER_090 Expected: Include invoice number Actual: Missing field | Low | Tester19 | 2025-12-23
200 | App crash when enabling biometric login | SRC_SECURITY_07 | TC_SEC_090 Expected: Enable biometrics Actual: Crash on enabling | High | Tester20 | 2025-12-23